## ProductBacklog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | USER STORIES | SCRUM TEAM ASSIGNED | STATUS | REMARK
1 | HIGH | USER01 | REGISTRATION | A TEAM | COMPLETED
2 | MEDIUM | USER02 | LOGIN FEATURE | B TEAM | IN PROGRESS
3 | HIGH | USER03 | DASHBOARD | C TEAM | COMPLETED
4 | HIGH | USER04 | MOVIEIST | D TEAM | IN PROGRESS
5 | HIGH | USER05 | SEAT SELECTION | E TEAM | IN PROGRESS
6 | HIGH | USER06 | PAYMENT | F TEAM | IN PROGRESS
7 | HIGH | USER07 | LOCATION | G TEAM | IN PROGRESS

## SprintBacklog1
USER STORY ID | USER STORY NAME |  |  | USER STORY STEP DEFINITION |  | ASSIGNED TO | ESTIMATE | ACTUAL TIME
|  |  | AS A < YPE OF USER> | I WANT TO < PERFORM SOME TASK> | SO THAT I CAN < ACHIEVE>
USER01 | registration |  | as a user | I want to create registration | so that I can get the details of user to create an account and for authentication purpose | A perosn | 2 hrs | 2 hrs
user02 | login |  | as a user | I want to create login | so that while logging in his details authenticated and his data appears | B person | 3 hrs
user03 | dashboard |  | as a user | I want to create dashboard | so that every option will visible to tap and can get more options | C person | 8 hra
USER04 | movielist | as a user |  | I want to create movie list | so that recently released movies which are playing in the theaters will aperar | D person | 2hrs
USER05 | seat selection |  | as a user | I want to create seat selection | so that they can select from which they are willing to watch | E person | 2 hrs
USER06 | payment |  | as a user | I want to create payment | so that after the successful payment then the ticket will confirm | F person | 6 hrs
USER07 | location |  | as a user | I want to create location | so that we can track the theater where it Is located | G person | 4 hrs

## SprintBacklog2
USER STORY ID | USER STORY NAME |  | USER STORY STEP DEFINITION |  | ASSIGNED TO | ESTIMATE | ACTUAL TIME
|  | AS A < YPE OF USER> | I WANT TO < PERFORM SOME TASK> | SO THAT I CAN < ACHIEVE>

## defect
Defect id | Defect issue | Created on | Creator | Assigned to | Severity | Priority | Stutus
D001 | Unable to search movie | 2024-07-06 | Nobitha | Doremon | High | High | open